## 2606_Validation
Category | Cookbook Link | Process TcxCliRequirement: teamcenterx== PipelineVariableVersion: '' TcXVersion: '' PipelineVersion: '' | Description | Type | Redo Post Deploy after TC Update Existing Env with New Patch | Expected time to complete | Oracle-Ent(BYOL)-HA Premium-tc2512.2025110700 25121711-prd ECA: 500126810 | PostSQL-SA Premium-tc2512.2025110700 25121811-prd ECA: 500126811 | Premium-tc2512.2025110700 25121711-prd4 ECA:500126812 | PRs reported | Notes
Dryrun Pre-requisites | Link | Vault Setup |  |  |  |  | Using Existing | Using Existing | Done
| Link | Vault integration with Kubernetes |  |  |  |  | Using Existing | Using Existing | Done
| Link | Vault Integration with Ansible |  |  |  |  | Using Existing | Using Existing | Done
| Link | Datadog (log aggregation, metrics, alerts) |  |  |  |  | Using Existing | Using Existing | Done
| Link | Create variable YAML for new AWS Account/XCR cluster |  |  |  |  | Using Existing | Using Existing | Done
| Link | Teamcenter X Enterprise Cloud Account (ECA) Setup |  |  |  |  | Using Existing | Using Existing | Done
| Link | Teamcenter X Customer SAM Account Set-up |  |  |  |  | Using Existing | Using Existing | Done
| Link | Enable the SAM accounts for ActAsRole Permissions |  |  |  |  | Using Existing | Using Existing | Done
| Link | Setup the actAsRole for the Admin SAM account to the Customer SAM account |  |  |  |  | Using Existing | Using Existing | Done
| Link | Generate SAMAuth, DSS, and SAM service user keys |  |  |  |  | Using Existing | Using Existing | Done
XAC DR SKU Onboarded
|  | ECA TC Author and Consumer DR SKU Association with CAD DR Synthetic SKUs | Dryrun Only
|  | Push CAD DR SKUs and changes to production SSC, which will include the fix for the entitlements | Dryrun Only
|  | Consume Recovery build in Git pipeline for Client Install Automation and new installers upload to Production SSC | Dryrun Only |  |  |  | NA | NA | NA
|  | Update all Ansible Template for H.Vault as User Input | Dryrun Only |  |  |  | Using Existing | Using Existing
Admin Console Configuration (UAT and Prod) |  | Admin console 1.6.3 Dryrun changes |  |  |  |  | Done | Done | Done
|  | Admin console 1.6.1 PROD changes |  |  |  |  | NA | NA | NA
|  | Entitlement API credentials so that multiple env support ACIS 1.5.3 lambda (UAT+Prod) |  |  |  |  | Using Existing | Using Existing
|  | Imort Ansible Template to RV Tower - Dryrun template 4.0.0 |  |  |  |  | Using Existing | Using Existing
|  | Import Ansible Template to Prod Tower - Prod template 4.0.0 |  |  |  |  | NA | NA
Tenant Onboarding | Link | Customer input (product IDs) | To trigger deploy pipeline | Ansible |  | 10 min | Done | Done | Done
| Link | Ansible playbook execution | To trigger deploy pipeline | Ansible |  | 8 hrs | Done | Done | Done
| Link | Successful Pipeline Output |  |  |  |  | Done | Done | Done
Post-Deploy | NA | Login to AWC URL with tcxadmin user |  | Manual | Yes | 5 min | Done | Done | Done
| Link | Trigger automated backup using ansible job template | EC2, RDS and EFS, Vault | Ansible | Yes | 140 min | Done | Done | Done
| Link | Modify the network to allow CAPS to perform AD join for CyberArk connection |  | Manual | No |  | NA | NA
|  | AD Join & outbound Endpoint etc. |  | Manual | No |  | NA | NA
| Link | Create Admin License Server object for Teamcenter X operating users |  | Manual | No | 10 min | NA | NA
| Link not available | Execute Delay Start Workflow using Ansible |  | Ansible |  | 10 min | Done | Done | Done
| Link | Increase Oracle database DBUSER_INDX tablespace size (Optional) |  | Manual | No | 10 min | NA | NA
| Link not available | Adjust the Oracle DB Maintenance Window |  | Manual |  | 5 min | NA | NA
| Link not available | Smoke Test Validations |  | Manual | Yes | 5 min | Done | Done | Done
| Link | Testing Virus Scanner on FSC
| Link | Uploading large file more than 2 gb without virus |  |  |  | 15 min
| Link | Uploading Large file more than 2 gb with virus
| Link | Uploading clean samll file less than 2 gb (100 mb) | Link |  |  | 2 min
| Link not available | MS Office Integration preference setup | Link | Manual | Yes | 5 min
| Link not available | Classification Manager Admin preference setup for TCx | Link |  |  | 5 min | Done | Done | Done
| Link not available | Updating TMS entry for Cloned/Updated Environments | Link | Manual | No |  | NA | NA | NA
| Link not available | VisServerFv Modifications | Link | Manual | Yes | 10 min | Done | Done | Done
| Link | Generate client metacache for RAC / CAD client to work in non English locale | Link | Manual | Yes | 45 min | Done | Done | Done
| Link not available | Configure Datadog to monitor system process logs | Link | Manual | No | 10 min | Done | Done | Done
| Link | Rich-Client Installation | Link |  |  | 60 min | Done |  | NA
| Link | Validate deployment success | Link |  |  | 5 min | Done | Done | Done
| Link | Import classification hierarchy in TcX Advanced | Link | Manual | No | 30 min | NA | NA
|  | Setup VPN from tenant env deploymentfor Azure | Link |  |  |  | NA | NA
|  | TCX Content Management/Content Management S1000D Runbook | Link |  |  |  | NA | NA
| Link | Teamcenter Dispatcher Installation | Link | Manual | Yes | 10 min | Done | Done | Done
| Link | Translators for TcX Standard and Advanced | Link | Manual | Yes | 30 min | NA | NA
| Link | Microsoft Office Installation | Link |  |  | NA | NA | NA
| Link | Teamcenter Visualization Installation | Link |  |  | 30min | Done | Done | Done
| Link | Requirements Management Translators Setup | Link |  |  | NA | NA | NA
| Link | Teamcenter Dispatcher Integration with NX | Link |  |  |  | Done | Done | Done
| Link | NX Installation | Link |  |  | 45 min | Failed | Failed | Failed
| Link | Edit translator.xml | Link | Manual | Yes | 20 min
| Link | Edit nxtransdirect.bat | Link | Manual | Yes | 20 min
| Link | NX Translation Test for TcX Essentials and Premium | Link |  |  |  | NA | NA
| Link | NX Translation Test for TcX Standard and TcX Advanced | Link |  |  |  | NA | NA
| Link not available | Teamcenter Dispatcher Integration with Solid Edge | Link
| Link not available | Solid Edge Installation | Link |  |  | 30 min
| Link not available | Configure Teamcenter Environment | Link |  |  | 5 min
| Link not available | Import Solid Edge Template | Link |  |  | 10 min
| Link not available | Dispatcher Configuration for Solid Edge | Link |  |  | 45 min
| Link | Teamcenter Dispatcher Integration with CatiaV5ToJtDirect Translator | Link
| Link | Troubleshoot Dispatcher Translator Failures | Link
| Link | Upgrade NX Dispatcher | Link
| Link not available | ECAD Translator | Link |  |  | NA | NA | NA | NA
| Link | Post Deploy and Validation Steps for Teamcenter X Products | Link | Manual | No |  | Done | Done | Done
| Link | Validation Steps for SolidWorks Integration | Link | Manual | No | 10 min | Done | Done | Done
| Link | Validation steps for Teamcenter Active Assistant | Link | Manual | No | 10 min | Done | Done | Done
| Link | Post Installation Steps for Creo Integration | Link | Manual | No |  | Done | Done | Done
| Link | Post Deploy Steps for AutoCAD Integration | Link | Manual | No |  | Done | Done | Done
| Link | Post Deploy Steps for Inventor Integration | Link | Manual | No |  | Done | Done | Done
| Link | Validation steps for Altium Integration | Link | Manual | No | 5 min | Done | Done | Done
| Link | Validation steps for Cadence Allegro | Link | Manual | No | 10 min | Done | Done | Done
| Link | Validation steps for Cadence Orcad | Link | Manual | No | 10 min | Done | Done | Done
| Link | Validation steps for AutoCAD or AutoCAD Electrical | Link | Manual | No |  | Done | Done | Done
| Link | Validation steps for CATIA v5 | Link | Manual | No |  | NA | NA | Done
| Link | Validation steps for CATIA V6 TC630605-XT |  |  |  |  | NA | NA | NA
| Link | Validation steps for PolarionX (WIP) |  | Manual | Yes | NA | NA | NA | NA
| Link | Substance Compliance and Compliance Process Manager (CPM) Deployment | Link | Manual | Yes | NA | NA | NA | NA
| Link | Product Configurator Deployment | Link | Manual | Yes | 5 mins | Done | Done | Done
| Link | TC X NX Part Manufacturing Integration Validation Steps |  |  |  | NA | NA | NA | NA
| Link | Check PAX Items |  |  |  | NA | NA | NA | NA
| Link | Check Manufacturing Template Items |  |  |  | NA | NA | NA | NA
| Link | Check Resources and Activities in Part Manufacturing Tab |  |  |  | NA | NA | NA | NA
| Link not available | Teamcenter Integration with Mendix WIP |  | Manual | Yes | NA | NA | NA | NA
| Link | Teamcenter Integration for ECAD Library |  |  |  | NA | Hold | Hold | Hold
| Link | Content Management and Content Management S1000D Deployment and Post Installation Steps |  |  |  |  | Hold | Hold | Hold
| Link | Validation steps for Machine Builder |  |  |  |  | Hold | Hold | Hold
|  | Validation steps for Methodics Integration |  |  |  |  | Hold | Hold | Hold
|  | Teamcenter Integration for SysML v2 |  |  |  |  | Hold | Hold | Hold
| Link | Enable Xcelerator Admin Console for Teamcenter X |  | Manual | No | 30 min | Done | Done | Done
| Link | Enable Admin console to assign users |  |  |  | 5 min | Done | Done | Done
| Link | Create CApS users in Teamcenter: Automated Script approach |  |  |  | 10 mins | NA
| Link |  |  | Manual | No | 5 mins | Done | Done | Done
| Link | Creating User in SAM Account |  |  | No | 5 mins | Done | Done | Done
| Link | Creating User in Teamcenter |  |  | No | 5 mins | Done | Done | Done
| Link | Creating User in LDAP |  |  | No | 10 mins | Done | Done | Done
| Link | Shutdown and restart workloads |  | Manual | Yes | 10 min | Done | Done | Done
| Link | Changing a configuration via pipeline variable |  | Manual | No
| Link | How to update Site Preference |  | Manual | No | 10 min | Done | Done | Done
| Link | Build AW client artifacts (awbuild) |  | Manual | No | 30 min | Done | DOne | DOne
| Link | LDAP configuration for additional admin users to be added (Optional - Needed only for SSO & Management Console) |  | Manual | No | 15 min | Done | DOne | DOne
| Link | LDAP configuration for additional non-admin users to be added (Optional - Needed only for NON-PROD) |  | Manual | No | 15 min | Done | Done | DOne
| Link | Configure Admin License Server for Teamcenter X operating users |  | Manual | No | 10 min | NA
| Link | Indexing after a data load operation |  | Manual | No |  | Done | Done | Done
|  | Adding additional modules/products on existing deployments |  | Manual | No | 8 hrs | In Progress
Environment Tier Transition
| Link | Rotating expired vault credentials in Ansible |  | Manual | No | NA | NA | NA
| Link | commands to start and stop dc services on linux |  | Manual | No | 5 mins | Done | Done | Done
| Link | Modify DB parameters for performance tuning |  | Ansible | Yes | 5 mins | Done | Done | Done
| Link | Deactivate a user |  | Manual | No | 5 min | Done | Done | Done
|  | POSTGRES_Encoding_Settings_for_tcprofilevars copy |  |  |  |  | NA | Done | Done
|  | Clam AV timeout settings for large files upload |  |  |  |  | Done | Done | Done
|  | Change EFS Throughput settings for large files upload |  |  |  |  | Done | Done | Done
| Link | Manual Istio Version Upgrade |  | Manual | No | NA | NA | NA
| Link | Manual update of Kubernetes labels |  | Manual | No | NA | NA | NA
| Link | Start Classification AI |  |  |  |  | NA | Hold
|  | VM Resize Operation |  |  |  | 20 min | Done | Done
| Link not available | Gitlab Access Token Rotation Operation |  |  |  |  | NA | NA
| Link | Updating an Existing Deployment |  | Manual + Ansible | No | NA | NA | NA
| Link | Upgrading an existing Deployment |  | Ansible | No | NA | NA | NA
| Link | Password Maintenance |  | Manual | No | 60 min | Blocked
| Link | Environment Termination-Cleanup/Teardown |  | Ansible | No | 120 mins | Done | Done
| Link | Trigger automated backup using ansible job template |  | Ansible | No | 120 min | Done | Done | Done
| Link | Schedule Automated Backup |  | Ansible |  | 100 min | Done | Done | Done
| Link | TcX environment shutdown |  | Ansible | No | 120 min | Done | Done | Done
| Link | Get Backup Set Id for Restoration |  | Ansible | No | 5 min | Done | Done | Done
| Link | Backed up Items that will be restored |  | Manual | No | 15 min | Done | Done | Done
| Link | Restore AWS resources using Ansible Trigger |  | Ansible | No | 60 min | Done | Done | Done
| Link | TcX environment restart |  | Ansible | Yes | 10 min | Done | Done | Done
| Link | Schedule Automated Retention
| Link | Troubleshooting |  | Manual | No
| Link | Deployment and Configuration Steps for Additional/Optional Products and Integrations |  | Manual | No |  | NA | NA
| Link | DevOps Team Operations |  | Manual | No |  | NA | NA
| Link | Hashicorp Vault access for operator users |  | Manual | No | 30 min
| Link | References |  | Manual | No
| Link | Appendix |  | Manual | No
| Link | Smoke Test Validations |  | Manual | Yes | 4 hrs
|  | Additional PID from existing |  | Manual | No
|  | Non existing random number PID - Negative use case |  | Manual | No
| Link | Applying personalization to a new deployment |  | Manual | No |  | NA | NA
| Link | Applying personalization to an existing deployment |  | Manual | Yes |  | Done | Done | Done
| Link | Applying personalization updates to an existing deployment |  | Manual | Yes
| Link | Merging admin data to existing BMIDE project for datamodel changes |  | Manual | No
| Link | Create a standalone software package for admin data |  | Manual | No
|  | Add Self Service Admin (SSA) and perform User management |  | Manual | No | 15 min
|  | Validate Self Service Admin use cases |  |  |  | 15 min
|  | Validate Admin Console Bulk Import |  |  |  | 10 min
|  | How to save / download logs |  | Manual | No
|  | How to change logging level |  | Manual | No
Optional Product Integrations | Link | Teamcenter X Essentials |  |  |  |  | NA | NA
| Link | Configure For SolidEdge X Support |  |  |  |  | NA | NA
| Link | Configure SolidWorks or SolidWorks Enterprise Integration |  |  |  |  | NA | NA
| Link not available | Configure PolarionX Integration |  |  |  |  | NA | NA
| Link | Multi-Site Deployment |  |  |  |  | NA | NA
| Link | Partner Connect Deployment |  |  |  |  | NA | NA
| Link | Supplier Connect Deployment |  |  |  |  | NA | NA
| Link | Customer VPN -TCX Resource setup Cookbook |  |  |  |  | NA | NA
| Link | Upgrading an Existing Teamcenter X Essentials Deployment |  |  |  |  | NA | NA
Std-Adv Overlay Deploy |  | Readiness of X-Navigator Deploy Package for STD/Advanced | New | Manual | Yes |  | NA | NA
Licensing | Link | License Configuration |  | Manual | No
| Link | License Configuration for the Initial Installations |  | Manual | No
| Link | Upload License file to common SA |  | Manual | No
| Link | Teamcenter X Cloud License for Production deployment
| Link | Teamcenter X Cloud License |  | Manual | No
| Link | License Replacement |  | Manual | No
Client Install Automation Validation |  | Connection Manager |  | Manual | No | 15 min
|  | NX |  | Manual | No | 60 min
|  | Solid Edge [SEEC] |  | Manual | No | 30min
|  | Solid Works [SWIM] |  | Manual | No | 30 min
|  | AutoCad [TCAA] |  | Manual | No
|  | Inventor [TCAI] |  | Manual | No
|  | Office |  | Manual | No | 30 min
|  | Creo [IPEM] |  | Manual | No
Replica Env Creation Full and Partial |  | Setup SA Prod Source Env with all post deploy steps completed |  | Ansible | No |  | Done | Done | Done
| Link | Full- Workflow- Create Full Clone Replica Environment |  | Ansible | Yes |  | Done | Done | Done
| Link | Full - Post replica deployment |  | Ansible | Yes |  | Done | Done | Done
| Link | Partial - Test Data Creation in Production Environment |  | Ansible | Yes |  | Done | Done | Done
| Link | Partial - Launch Workflow |  | Ansible | Yes |  | Done | Done | Done
| Link | Partial - Approval Stage |  | Ansible | Yes |  | Done | Done | Done
| Link | LDAP Sync
| Link not available | Full and Partial - Replica Smoke Test Validations |  | Manual | Yes |  | Done | Done | Done
Datadog | Link | Datadog - AWS integration |  | Manual | No
SRE Onboarding operations
| Link not available | Customer addition onboarding |  | Manual | No
| Link not available | Customer offboarding |  | Manual | No
Datadog Billing | Link | TcX Reports Configuration |  |  |  |  | NA | NA
| Link not available | TcX Usage Reports |  |  |  |  | NA | NA
| Link not available | TcX Billing Report |  |  |  |  | NA | NA
XApps Integration | Link not available | SAMAuth Application registration to generate client_id and secret for XShare apps |  |  |  |  | NA | NA
| Link | xApps Integration with Teamcenter X |  |  |  |  | NA | NA
| Link | Initial Setup Requirements |  |  |  |  | NA | NA
| Link | About xAppIssuers and xAppUsers |  |  |  |  | NA | NA
| Link | Bootstrapping a New Deployment |  |  |  |  | NA | NA
| Link | Rerun or Update or Upgrade Existing TCX Deployments
| Link | Sharing the TCX clientID with other xApps for Whitelisting |  |  |  |  | NA | NA
Remove this steps from WBS |  | Steps For Observability |  | Manual |  |  | NA | NA
|  | Alerts/SLO setup |  | Manual |  |  | NA | NA
|  | Synthetics test setup |  | Manual |  |  | NA | NA
|  | Runbooks Readiness |  | Manual |  |  | NA | NA
|  | Pager Duty Setup |  | Manual |  |  | NA | NA
|  | Internal facing status page |  | Manual |  |  | NA | NA
|  | External facing status page |  | Manual |  |  | NA | NA
|  | Test of the alerts and pager duty setup |  | Manual |  |  | NA | NA
Runbook Validation |  | SRE Runbook TCX_Webtier_Issues.pdf |  | Manual |  |  | NA | NA
|  | SRE-RunBook_failed_to_assign_tc_server.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_AWbuild_Service.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_Dispatcher.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_FMS_Service.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_LDAP.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_License_Server.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_PoolManager_Service.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_SelfAdmin.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_SOLR.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_SSO_Service.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_To Start Visualization Services.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-Runbook_User_Credentails_Not_Working.pdf |  | Manual |  |  | NA | NA
|  | SRE-TCX-RunBook_Visualization_Server_Issues.pdf |  | Manual |  |  | NA | NA
|  | SRE_TCX_Runbook_TC_Integration_for_NX.pdf |  | Manual |  |  | NA | NA
Tenant and ECA Cleanup |  | Tenant cleanup | ECAs used by NX X, Tc X, CX and all other teams need to be cleaned up | Manual |  |  | NA | NA
|  | ECA cleanup (incl. Admin console) |  | Manual |  |  | NA | NA
|  | Infrastructure cleanup | Matt Anderson / Girish to prioritize | Manual |  |  | NA | NA
Offboarding |  | Ansible template (move to Prod) | Business process and technical steps for offboarding | Manual |  |  | NA | NA
|  | Test customer offboarding |  |  |  |  | NA | NA
Ops Enablement |  | TcX-S, A, P enablement |  | Manual
Ops Handover |  | Create ECAs and ECA admins |  | Manual
|  | Create two tenants, and smoke test |  | Manual
|  | SAM Operating Account ownership |  | Manual
|  | Setup support engineers from NX X and Teamcenter X product teams |  | Manual
|  | Production Infrastructure sizing/Resizing |  | Manual
|  | Create Backup schedule |  | Manual
|  | Create OS Patch schedule |  | Manual
|  | Create Application Patch schedule and procedure |  | Manual
CX Testing |  | CX Testing Setup
|  | Create Tenants and Add Users |  | Manual